Department of Computer Science, CUI Lahore Campus

|  | Assignment = Quiz 2 |
| --- | --- |

| Name: | Section: | Course Title: Software Project Management | Date: |
| --- | --- | --- | --- |
| Reg.#: | Instructor: Sana Rizwan | Marks: 5 | Class/Batch: |

Instructions

- DO NOT copy the assignment, marks will be graded on originality of work, zero mark will be for copied one. Assignment will be checked by Plagiarism software

- Each question has 01 mark

- Submission date is 19th April 2020 (Sunday)

- Submit the assignment using MS Word individually. Image file is not acceptable.

- Submit the assignment before closing date on Microsoft Teams.

Question 1:

Draw the Network Diagram shown activities on arrows (AOA).

Question 2:

Draw the ADN Diagram shown activities on arrows (AOA).

Question 3:

| Activity | Preceding Activity | Normal Time (Days) |
| --- | --- | --- |
| 1-2 | -- | 20 |
| 1-3 | -- | 25 |
| 2-3 | 1-2 | 10 |
| 2-4 | 1-2 | 12 |
| 3-4 | 1-3 , 2-3 | 5 |
| 4-5 | 2-4 , 3-4 | 10 |

Draw activity network diagram and identify the time allocation.

Question 4:

| Activity | Optimistic Time | Mostly Likely Time | Pessimistic Time |
| --- | --- | --- | --- |
| A | 4 | 10 | 16 |
| B | 3 | 6 | 9 |
| C | 4 | 7 | 16 |
| D | 5 | 5 | 5 |
| E | 8 | 11 | 32 |
| F | 4 | 10 | 16 |
| G | 2 | 5 | 8 |

Calculate Expected Mean Duration, variance and Standard Deviation of each activity.

Question 5:

| Activities | Predecessors | to | tm | tp |
| --- | --- | --- | --- | --- |
| A | -- | 6 | 9 | 12 |
| B | A | 14 | 17 | 20 |
| C | A | 7 | 10 | 13 |
| D | A | 3 | 5 | 9 |
| E | -- | 4 | 7 | 8 |
| F | E | 9 | 11 | 12 |
| G | C,F | 10 | 14 | 16 |
| H | F,G | 17 | 20 | 25 |
| I | C | 12 | 15 | 18 |
| J | B | 13 | 18 | 25 |

- Draw the ADN network diagram for Pert.

- Find the Expected mean duration and variance for each activity

THE END